## Capabilities
Id (R/O) | Title* | Description* | Primary Program* | Additional Programs | State* | Parent Epic* | Theme | Blocked (R/O) | Process Step | Owner | Type* | Releases | Strategic Driver | Rank | Investment | Strategic Value Score | MVP | Tags | Portfolio Ask Date | Start / Initiation Date | Target Completion Date | Acceptance Criteria (R/O) | Features (R/O) | Team Weeks | WSJF Values | T-Shirt | Points | Story Points (R/O) | WSJF Prioritization(R/0)
4491 | Topology post 1.0 - Enhancements (Spillover DSPF-834) | Summary As an orchestrator user, I want to see detailed resource information directly connected to nodes and resources in the topology view, so that I can quickly understand resource allocation, utilization, and relationships without navigating to separate screens. Problem Statement Currently, the topology view displays nodes and resources in a hierarchical structure but lacks integrated resource information such as utilization metrics, configuration details, and status. Users must click away from the topology to access this critical information, breaking their workflow and reducing operational efficiency. Why it matters This enhancement matters because effective orchestration across manufacturing, retail, and banking environments requires immediate visibility into resource details within the context of the topology. Without this integrated view, users spend excessive time switching between views, increasing the risk of overlooking important resource constraints or misconfigurations during deployment planning and troubleshooting. Target customer / specific use cases Solution Architects : Need to verify resource allocation matches architectural requirements DevOps Engineers : Need comprehensive resource context when modifying deployments System Administrators : Require quick access to resource configuration details when troubleshooting Customer & business value statement This feature will reduce time spent gathering resource information by 40%, improve decision-making accuracy by 30%, and enable faster issue resolution by connecting all relevant resource data directly to the visual topology representation. Success Metrics 40% reduction in time spent navigating between topology and resource detail views 35% faster identification of resource-related issues 25% improvement in resource allocation efficiency 20% increase in user satisfaction with topology functionality Requirements Smart Group: visual grouping by : DBs, compute, apps, group by infra layer (HW → Hypervisor → VM → App) Side Panel that displays detailed information when hovering/clicking on topology elements For node type distinguishes physical from virtual Live resource metrics (CPU, memory, storage, network) visible directly on topology elements. Contextual filtering to show only resources matching specific criteria Filters for: Node type Status Labels/tags Resource tagging and categorization visible in topology Align Outcome Team with Topology Example : I deployed my blueprint (vmware-blueprint)] ↓ Dell Server (baremetal node), Powerstore,) ↓ VMware ESXi / vCenter - with hyperlink ↓ Group- VM (virtual machine) with the nodes related (binary, images, network) ↓ Group App Layer: NGINX / App Server Usability Consistent information display format across all resource types Progressive disclosure of resource details (basic info on hover, detailed on click) Visual indicators that scale appropriately with topology zoom level Customizable resource information panels based on user preferences Keyboard shortcuts for quick access to resource details Search functionality that highlights matching resource attributes in topology Color-coded resource status that is accessible for color-blind users Responsive design for resource information displays across device sizes Ability to pin important resource information for persistent visibility Reliability Graceful degradation when resource metrics are temporarily unavailable Cached resource data with clear timestamp for last update Background refreshing of resource data without disrupting the user interface Consistent performance regardless of the number of resources displayed Fallback display options when detailed metrics cannot be retrieved Data validation to identify and highlight potentially incorrect resource information Supportability Detailed logging of resource data retrieval and display events Admin controls to configure which resource metrics are displayed by default Customizable resource thresholds for status indicators Documentation for extending resource information types Troubleshooting guide for resource data integration issues Version control for resource information display templates Telemetry Track which resource information users access most frequently Measure time spent viewing resource details within topology Record frequency of resource filtering and comparison actions Monitor resource data refresh performance Collect user customization patterns for resource information displays Security Requirements Resource information visibility controlled by user permissions Sensitive resource data masked based on user role Audit logging for access to detailed resource information Secure storage of resource credentials for metric collection Role-based controls for resource configuration actions Data sanitization for all resource information displays Dependencies Integration with resource page Topology rendering engine updates to support smart groups- Solution (BV is 8 + TV is 13 + RR/OE is 8) / Job Size is 5) 5.8 WSJF | DAP Service Orchestration PT |  | 1 - Not Started | Simplify Orchestration UX and Engine | Dell Automation Platform (Core) | No | In Refinement | Dainy_Lev@Dell.com | Business | Solutions Platform CY25Q3 |  | 32 |  | 1 | No | Solution,UI,Outcome,DOR-Epic-Created |  |  |  | ~1. 25029 Users can view essential resource information (status, utilization, configuration) directly in the topology view Resource status is clearly indicated through visual cues in the topology Users can filter the topology view based on resource attributes | 1. [DOR] [4491] Topology post 1.0 - Enhancements (Spillover DSPF-834) 2. 4491 - UX Design 3. 4491 - UX Validation 4. Enhance Topology view with node details for resource monitoring and management | 0 | 8, 13, 8, 5 | No estimate | 0 | 0 | 5.8
5647 | [Blueprint] Upload Option from an External Repository | Summary : As a user, I want Orchestrator to connect to an external repository, so that I can upload blueprints/images from repositories like GitHub and streamline version control and collaborative development workflows. Problem Statement : Currently, users cannot directly connect Orchestrator to external repositories for uploading blueprints/images. This feature will enable users to link their GitHub repositories, select specific blueprints or configurations, and upload them directly into Orchestrator for further processing and management. This integration will enhance workflow efficiency and collaboration. Target Customer / Specific Use Cases: Target customers include IT Managers, Data Centers Operators, and Systems Administrators managing diverse hardware environments. These users will benefit from streamlined integration with version control systems, reducing manual upload processes and improving collaborative development. Success Metrics: Increased adoption and usage of the external repository integration feature. Reduction in manual upload errors. Improved user satisfaction and workflow efficiency. Requirements: When user navigates to the Orchestrator > Inventory > Blueprints section and click on More Actions > Upload from external repository, it should present a modal with: External Repo List: The system must fetch and display a list of repositories that the authenticated user has access to from GitHub. Branch Listing for Blueprint Repositories: The system must fetch and display a list of active branches from the selected repository. File and Directory Selection for Blueprints: The system must allow the user to navigate the directory structure of the selected repository and branch, enabling selection of specific blueprint files or directories for upload. Blueprint Upload Initiation to Orchestrator: The system must allow the user to initiate the upload of selected blueprint files or directories to the blueprint management system. Blueprint Upload Progress Tracking: The system must display the progress of the upload, including the status of individual files. Blueprint Upload Completion Notification: The system must notify the user upon the successful completion of the upload and display the newly uploaded blueprints in the system. Error Handling for Blueprint Upload: The system must handle errors gracefully, providing appropriate messages and options to retry or troubleshoot issues. Logging of Blueprint Upload Activities: The system must log all upload activities, including initiation, progress, completion, and any errors encountered. Usability: Ensure the repository connection and upload process are intuitive and easy to use. Provide clear visual feedback and guidance to users during the upload process. Reliability Ensure the repository connection and upload features are robust and reliable, minimizing downtime and errors. Supportability: Provide documentation and support for users to understand and utilize the external repository integration effectively. Telemetry: Not applicable for this feature. Security Requirements: Authentication Support: GitHub (Personal Access Token, GitHub Token). Ensure authentication tokens are stored securely in the Vault and implemented via the Secrets mechanism. Data in Motion: Utilize TLS for encrypted end-to-end communication between EO and external repositories. Customer Notification: Present a warning notification before starting the upload of the blueprint file, informing the customer of their responsibility for the hygiene of files/images on the external repository. This notification is not required for Dell repositories used for download only. Virus Total Integration: Integrate the blueprint upload mechanism with the Virus Total framework to evaluate blueprints/images files. File Type Validation: Evaluate file structure validation according to supported file types and allow uploading only particular types (Types - TBD). Audit Log: Log any interactive manipulations of EO users, including configuring, removing, editing external repository connections, and uploading blueprint files. RBAC: Note: keep current permissions for Deploy Operations Administrators Application Admin Operational Manager Viewer Deploy X X Dependencies: Integration with existing blueprint catalog systems. Compatibility with existing APIs. Access to APIs for node management to create or specify existing nodes. 20/05/2025 (BV is 8 + TV is 8 + RR/OE is 8) / Job Size is 5) 5/27/2025 (BV is 8 + TV is 8 + RR/OE is 8) / Job Size is 5) 4.8 | DAP Service Orchestration PT |  | 1 - Not Started | Simplify Orchestration UX and Engine | Dell Automation Platform (Core) | No | In Refinement | Dainy_Lev@Dell.com | Business | Solutions Platform CY25Q3 |  | 39 |  | 1 | No | UI,DOR-Epic-Created |  |  |  | ~1. 13932 Given a user wants to upload a blueprint from an external repository, When the user navigates to the upload section, Then the system should display an option to link an external repository (e.g., GitHub). Repository Authentication for Blueprints Given a user wants to link a GitHub repository, When the user provides the repository URL and authentication details (Supported Authentication options be presented) Then the system should validate and securely store the authentication details in Vault. Then the system should use a secret mechanism to authenticate with supported external repositories. Blueprint Repository Selection Given a user has authenticated with GitHub, When the user views their repositories, Then the system should display a list of the user’s repositories from GitHub for selection. Blueprint Branch Selection Given a user has selected a repository, When the user views branches, Then the system should display a list of branches from the selected repository for further selection. Blueprint File Selection Given a user has selected a repository and branch, When the user views the repository content, Then the system should display the directory structure and allow the user to select specific blueprints or configuration files to upload Blueprint Upload Confirmation Given a user has selected files or directories, When the user initiates the upload, Then system shall raise a notification regarding customer responsibility for files stored in an external repository. Then EO user shall confirm that he agrees. Then the system should confirm the action and start uploading the selected content to the blueprint management system. VirusTotal integration Given a user has selected files or directories When the user initiates the upload Then the system shall validate the selected files for being a malicious files via VirusTotal framework | 1. [DOR] [5647] [Blueprint] Upload Option from an External Repository 2. Add support for Orchestrator to connect to external repository 3. Enable the ability to securely upload blueprints that reside in an external repository 4. Sucurely Upload one or more image files from an external repository. | 0 | 8, 8, 8, 5 | No estimate | 0 | 0 | 4.8
8773 | [Deploy Wizard] - Simplify process for Clusters & Outcomes -(spillover DSPF-798) | Summary As a private cloud administrator, I want to simplify the deployment of blueprints on clusters through an intuitive wizard interface, so that I can efficiently scale applications across my infrastructure without struggling with complex configuration form. Problem Statement The current blueprint deployment wizard is not user-friendly and creates significant friction for private cloud administrators. Specific issues include: Input fields lack sufficient help text and contextual guidance Raw JSON strings are exposed to users, requiring manual editing and technical expertise The configuration process presents an overwhelming number of fields in a single, lengthy form Critical configuration options are difficult to identify among numerous less important settings Lack of input validation leads to frequent errors that are discovered only during deployment These usability issues force administrators to spend excessive time on deployment configuration, increase the likelihood of errors, and create dependency on specialized technical resources. Even experienced administrators struggle to efficiently navigate the deployment process, resulting in delays, frustration, and underutilization of the platform. By redesigning the wizard with user-centric principles, we can dramatically reduce the cognitive load, technical knowledge requirements, and time investment needed for blueprint deployments. This directly impacts operational efficiency, resource utilization, and the organization's ability to quickly respond to business needs through rapid application deployment. Target customer / specific use cases Private cloud administrators managing multi-tenant environments IT operations teams responsible for application scaling DevOps engineers managing containerized workloads Requirements Users must be able to view and manage a combined list of available servers. Configuration Options: The system should display existing nodes for selection The deployment process should continue seamlessly after servers and clusters are configured, allowing users to select an appropriate blueprint from the catalog. Validation for Minimum requirements provided by the BP - If minimum it's not met then should be rejected from compute svc Wizard with logical grouping of related configurations. Fix inputs that has JSON abstraction layer (see example attached on McQueen mail) Configuration templates for common deployment scenarios Real-time validation with specific error messages and resolution suggestions Conditional groups shows/hides relevant configuration options Usability Redesigned wizard with clear step-by-step workflow Comprehensive inline help text with examples for each configuration field Search functionality to quickly locate specific configuration options Visual indicators for required vs. optional settings Visual feedback for valid/invalid configurations before submission Configuration summary view before final deployment Reliability Compatibility verification with target cluster environments Configuration preset validation against best practices Supportability Configuration import inputs value Automated documentation generation based on configurations Configuration history with comparison capabilities Telemetry Configuration time metrics by wizard section Error frequency by configuration field User interaction patterns within the wizard Configuration variance analysis across deployments Help text Security Requirements Secure handling of sensitive configuration parameters Role-appropriate configuration visibility and modification rights Configuration audit trails with change tracking Secure parameter suggestions that follow compliance guidelines Authentication verification before configuration submission Dependencies Access to cluster specification repository Authentication and authorization services Blueprint schema definition https://confluence.cec.lab.emc.com/display/ISGPDE/Cluster+citizen+notes Existing validation rule engines (BV is 13 + TV is 8 + RR/OE is 13) / Job Size is 5) 6.8 WSJF | DAP Service Orchestration PT |  | 1 - Not Started | Simplify Orchestration UX and Engine | Dell Automation Platform (Core) | No | In Refinement | Dainy_Lev@Dell.com | Business | Solutions Platform CY25Q3 |  | 13 |  | 1 | No | Outcome,UI,DOR-Epic-Created |  |  |  | ~1. 25146 New users can successfully configure their first deployment without consulting documentation System automatically validates and prevents common configuration errors Users never need to manually edit JSON for standard configuration scenarios Configuration wizard adapts to show only relevant fields based on previous selections Configuration process provides clear guidance at each step Users can easily locate and modify specific configuration parameters Wizard maintains full configuration capabilities while simplifying the user experience | 1. [DOR] [8773] [Deploy Wizard] - Simplify process for Clusters & Outcomes -(spillover DSPF-798) 2. Add Telemetry support for user experience information 3. Add Wizard supportability features 4. Enable sescure configuraiton and use of the deployments 5. Enhance the deployment wizard with simplified options for clusters and DAP Outcomes. | 0 | 13, 8, 13, 5 | No estimate | 0 | 0 | 6.8
9305 | Creation and cleanup of paid DAP tenant | Summary As an DAP tenant Systems Administrator, I want to start a new paid DAP instance after completing my Initial registration , so that I can deploy a clean production environment while ensuring my Initial registration data is securely deleted. Problem Statement Customers who complete the DAP registration would want to go with paid outcome and not migrate their existing configurations (example, user data). This is often due to the need for a clean production environment or because the initial registration functionalities was used for evaluation and experimentation. However, there is currently no guided process to provision a new paid instance while ensuring secure deletion of the Initial registration environment. This gap can lead to confusion, data retention concerns, and operational delays. Providing a clear, secure, and user-friendly path to start fresh enhances trust and improves the onboarding experience. Target Customer and Use Cases Target Customers: Customer DAP instance Systems Administrators Dell Sales Representatives Dell ProDeploy Engineers Use Cases: A customer completes an Initial registration and decides to purchase a license for a new production environment, requiring a clean slate. A customer wants to ensure that all Initial registration and user data is securely deleted to meet internal compliance or security policies. A Dell Sales Representative assists a customer in provisioning a new paid instance post-Initial registration and needs a streamlined process to do so. Success Metrics 99.9% of new paid instances are provisioned within 30 minutes post-initial registration. 100% secure deletion of Initial registration data confirmed via audit logs. 20% increase in customer satisfaction scores related to onboarding and data handling. 10% reduction in support tickets related to Initial registration-to-paid transitions. Functionality Through the DSA tool, user has the option to initiate a new paid DAP instance from the portal afte r Initial registration expiration. Secure deletion workflow for the Initial registration instance, inc luding confirmation and audit logging and user data. License entry and validation process for provisioning the new paid instance. Notification system to inform users of successful provisioning of a Paid DAP tenant and successful deletion of the Initial registration. Usability MIRO: https://miro.com/app/board/uXjVI-Qqu9c=/ When the user goes through the DSA tooling for a new tenant to be created and requires no porting of existing data: Clear UI prompts guiding the user through the decision to start fresh or migrate. Confirmation dialogs and progress indicators for deletion and provisioning steps. Reliability 99.9% success rate for provisioning new paid instances. Secure deletion process must be verifiable and irreversible. Fail-safe mechanisms in case of provisioning or deletion errors. Supportability Documentation and support articles for starting a new paid instance post-Initial registration. Logs and telemetry available for support teams to troubleshoot provisioning or deletion issues. Support team training on common customer scenarios and workflows. Telemetry Track number of users choosing to start fresh vs. migrate. Monitor provisioning success/failure rates. Capture user feedback post-transition for continuous improvement. Security Requirements Only users with the Administrator role can initiate secure deletion and new instance provisioning of customer DAP tenants All deletion actions must be logged and auditable. Justification of deletion shall be presented to the customer Data must be securely wiped in compliance with Dell’s data handling policies. Dependencies Licensing service must be available and integrated with DAP. The provisioning backend must support new instance creation workflows. Secure deletion service must be compliant with data protection standards. Acceptance Criteria A user can choose to start a new paid DAP instance after the Initial registration expiration. The system securely deletes the Initial registration instance and confirms the action. A new paid instance is provisioned and ready for use. The user receives confirmation and access credentials for the new environment. WSJF 05/29/2025 - (BV is 8 + TV is 20 + RR/OE is 13) / Job Size is 8) 5.13 | DAP Service Orchestration PT |  | 1 - Not Started | Ensure Platform Foundational Enterprise Readiness | Dell Automation Platform (Core) | No | In Refinement | Maxim.Balin@Dell.com | Business | Solutions Platform CY25Q3 |  | 8 |  | 1 | No | DOR-Epic-Created |  |  |  | ~1. 27544 A user can start a new paid DAP instance after the Initial registration. The system securely deletes the Initial registration instance and confirms the action. A new paid instance is provisioned and ready for use. The user receives confirmation and access credentials for the new environment. | 1. [DOR] [9305] Creation and cleanup of paid DAP tenant | 0 | 8, 8, 13, 5 | No estimate | 0 | 0 | 5.8
9923 | Persistent View Preference Across Orchestrator | h3. *Summary* As a *Platform Engineer*, I want the platform to remember my preferred view (card or list) across all tabs, so that I have a consistent and personalized experience throughout the interface. h3. *Problem Statement* Currently, each tab (e.g., Blueprints, Deployments, Infraestructure) defaults to a predefined view—typically card view—regardless of the user’s previous selection. This forces users to repeatedly switch views when navigating between tabs, disrupting workflow and reducing efficiency. Remembering the user’s preferred view across all tabs enhances usability, reduces friction, and aligns with modern UX expectations. h3. Target Customer and Use Cases *Target Personas:* * Platform Engineer * DevOps Developer * IT Generalist L2 - Systems Administrator * Edge Solutions Architect *Use Cases:* * A DevOps Developer prefers list view for its compactness and uses it across Blueprints, Deployments, and Services. They expect the platform to remember this preference globally. * An IT Generalist working across multiple tabs wants a consistent interface without needing to reset the view each time. h3. *Functionality* * Store the following user preferences: ** View type (card or list) ** Column visibility and order ** Column width and sorting ** Panel layout and size (if applicable) * Automatically apply stored preferences when navigating to any tab. * Set *list view* as the default for new users or when no preference is stored. * Ensure any tab-specific popups or onboarding flows appear as expected. * Unified toggle control for switching views across all tabs. * Clear visual indication of the active view. * View preference persists across sessions, tabs, and browser reloads. * No additional configuration required from the user. h3. *Reliability* * View preference is stored reliably in local storage or backend user profile settings. * Fallback to default (list view) if preference data is unavailable or corrupted. * Tested across all supported browsers and devices. h3. *Supportability* * Minimal support overhead due to consistent implementation across tabs. * Centralized logic for managing view preferences simplifies maintenance. * Documentation includes a troubleshooting guide for view persistence issues. h3. *Telemetry* * Track view preference changes and usage across tabs. * Monitor which view is most commonly used per tab. * Log persistence failures or errors in applying stored preferences. h3. *Security Requirements* * No sensitive data is stored—only UI preference. * Accessible to all RBAC roles: ** *Administrator*: Full access. ** *Operational Manager*: Full access. ** *Application Manager*: Full access. ** *Viewer*: Full access. h3. Dependencies * Frontend framework support for local storage or user settings API. * Optional backend support if storing preferences server-side. * Consistent view toggle implementation across all tabs. | DAP Service Orchestration PT |  | 1 - Not Started | Simplify Orchestration UX and Engine | Dell Automation Platform (Core) | No | In Definition | Dainy_Lev@Dell.com | Business | Solutions Platform CY25Q3 |  | 0 |  | 1 | No | UPS |  |  |  | ~1. 29962 Users can switch views, hide/show columns, and adjust layouts on any tab. All layout and visibility preferences persist across tabs and sessions. List view is the default for new users or when no preference is stored. Preferences are applied automatically without user intervention. The feature works consistently across all supported browsers and devices. | 1. Add user preference views to the Orchestrator UI | 0 |  | No estimate | 0 | 0 | 0
9917 | Q3 Timebox tech debt | This is a placeholder of epics around tech debt. As agreed, the epics here should include only work that has no visible customer impact. The Epics should follow all the guidelines for duration (one sprint), DoR and DoD. *5/27/2025* ¦(BV is 13 + TV is 13 + RR/OE is 20) / Job Size is 20)2.3¦ | DAP Service Orchestration PT | DAP Blueprint Assist PT, DAP Catalog PT, DAP CICD PT, DAP Compute PT, DAP Infra Fleet Mgmt PT, DAP Ops PT, DAP Portal PT, DAP Security PT, DAP Serviceability PT, DAP System Test PT | 1 - Not Started | Ensure Platform Foundational Enterprise Readiness | Dell Automation Platform (Core) | No | In Definition | Christodoulos.Psaltis@dell.com | Debt | Solutions Platform CY25Q3 |  | 0 |  | 1 | No |  |  |  |  | None | 1. [DOR] test 3# Epic | 0 |  | No estimate | 0 | 0 | 0
9497 | DAP Outcome Update Framework | Summary As an IT Generalist L2 - Systems Administrator , I want to use a single workflow to achieve updates across offers, so that I can minimize complexity, cost, and time to market while maximizing flexibility and integration opportunities. Problem Statement Current update workflows are fragmented and lack integration, leading to increased complexity, higher costs, and longer time to market. A unified workflow is needed to streamline updates across various offers, accommodating existing and future advanced features without disrupting current workflows. Target Customer and Use Cases IT Generalist L2 - Systems Administrator : Needs a streamlined update process to manage multiple offers efficiently. Platform Engineer : Requires flexibility in update workflows to integrate with existing systems and future enhancements. HCI Implementer (L2 Systems Engineer) : Seeks non-disruptive updates to maintain system stability and performance. Success Metrics Reduction in update deployment time by 30%. Decrease in update-related incidents by 20%. Increase in user adoption of the unified workflow by 50%. Functionality Evaluate Phase : Runs health and compatibility checks, outputs results to the DAPO event stream. Stage Phase : Moves components to the necessary location for updates. Update Phase : Applies the latest recommended updates. Usability Primary modals triggered from DAPO Inventory>Infrastructure page Evaluate, where the user is able to configure health and compatibility checks Stage, where the user is able to pre-stage update bundles to the target Update, where the user is able to execute the update Secondary modals are triggered from primary modals: Desired State Inventory, where the user can view and manage different outcome configurations Desired State Configuration, where the user devices outcome configurations Settings, where the user sets overrides and bandwidth controls Schedule, where the user is able to schedule the task on a single or repeating basis Saveable Filters, where the user is able to create sets of devices which can be acted on collectively. Reliability Ensures non-disruptive updates to existing workflows. Preserves observability and controllability features of the VxRail workflow. Supportability Leverages existing offer APIs (NativeEdge, Private Cloud, PowerStore, PowerEdge). Provides support for future advanced features like health checks, staging, and bandwidth shaping. Telemetry Monitors update status and lifecycle (Up to Date, Critical Update Available, etc.). Allows users to save filters for quick fleet segmentation and monitoring. Security Requirements Role-Based Access Control (RBAC) with roles such as Administrator, Operational Manager, Application Manager, and Viewer. Dependencies Integration with existing offer APIs (DAP 1.1 for NativeEdge and Private Cloud). Future support for DCP RHOS, DCP Nutanix, PowerStore, and PowerEdge. Acceptance Criteria Users can perform health and compatibility checks during the Evaluate phase. Users can stage components for updates in the Stage phase. Users can apply updates in the Update phase. Users can monitor update status and lifecycle. Users can schedule updates immediately, at a future point, or on a recurring basis. (BV is 40 + TV is 13 + RR/OE is 13) / Job Size is 8) 8.25 WSJF 5/20/25 (BV is 13 + TV is 13 + RR/OE is 13) / Job Size is 8) 4.88 WSJF 5/9/25 | DAP Service Orchestration PT |  | 1 - Not Started | Shared Orchestrator features | Grow NativeEdge | No | In Refinement | Paul.Galjan@dell.com | Business | Solutions Platform CY25Q3 |  | 10 |  | 1 | No | LCM,UI,DOR-Epic-Created |  |  |  | ~1. 29967 Users are able to schedule healthchecks independently from the update process ~2. 29968 Users are able to schedule the Staging of updates independently of the update process ~3. 29969 Users are able to schedule the Update of heterogenous sets of objects from the Inventory when leveraging the recommended update paths ~4. 29970 A single schedule modal is available, allowing a robust set of scheduling options across EValuate, Stage, and Update ~5. 29971 The user may create an arbitrary number of custom, validated desired states ~6. 29972 User is able to control bandwidth consumed during the stage process by number of sessions and bandwidth consumed per session ~7. 29973 User is able to override errors on an ad hoc basis | 1. [DOR] [9497] DAP Outcome Update Framework | 0 |  | No estimate | 0 | 0 | 0